## Priority by park
Arden Manor Priorities List
Crabtree Park
| Item | Description | Cost
H | Irrigation | Replace all broken sprinklers, Replace drip line that is on the perimeter of the park that is currently broken, system flush. Currently working with Jensen on proposed plan and rebates. | TBD
H | Play Structures & sand box | Certified playground inspection needed, Play equipment has heavy use suggesting updated play equipment be installed, Rubber bark level is low and needs to be added, sand box needs sand added | TBD
M | Restroom | One restroom is currently out of order. Sink, toilet paper/paper towel dispensers, door and signage needs to be replaced or repaired. The roof needs to be re-shingled soon due to age. | TBD
L | Water Fountains | There are two water fountains at this park. The fountain by the restroom is not in working order and would need to be replaced. The fountain by the snack bar needs to be repaired. | TBD
L | Basketball Court | Hoop needs to be replaced on one metal post. Could make a full court if the hoops were moved and one backboard was replaced. Lines need to be repainted and nets need to be replaced. | TBD
L | Tennis Courts | The fence surrounding the tennis courts need some repairs. The tennis court needs new nets and the cracks in the court need to be repaired or possibly to be resurfaced. We would need to have a contractor to come out to advise the District on our options. | TBD
H | Baseball Field | The fence surrounding the baseball field needs some repairs. Some of the planks of wood used for fan benches and back stop need to be replaced. The infield needs to be cleared of all weeds and debris to be roto tilled. Before grading the field ball field mix would need to be added and spread out. The outfield needs to be leveled off and ruts filled in. If these repairs can be made before spring we could potentially generate revenue from renting out our field. | TBD
H | Trees | The trees need to be trimmed and thinned out with weight reduction. There are a few dead trees that need to be removed. | TBD
Arden Manor Priorities List
Deterding Park
| Item | Description | Cost
H | Irrigation | Replace all broken sprinklers and a system flush | TBD
H | Play Structures | Certified playground inspection needed, Rubber bark level is low and needs to be added. | TBD
L | Turf Field | The turf field needs holes and missing sections to be replaced and repaired. Signage needs to be posted to prohibit the use of cleats on the field. | TBD
M | Water Fountain | The water fountains is not in working order and needs new parts so that both drinking bowls can be used. Depending on what is found we may need a new fountain. | TBD
H | Concrete Sidewalk | Areas by the main office and the park side of the pool exit gate need to be patched and painted red to remove any tripping hazards. | TBD
H | Trees | The trees need to be trimmed and thinned out. There are a few dead trees that need to be removed. The large eucalyptus tree needs to have 25% trimmed off to reduce weight. | TBD
Deterding Pool Complex
| Item | Description | Cost
M-H | Small Pool Resurfaced | The small pool needs to be resurfaced due to wear and tear from usage. The bottom of the pool is very porous. Each season is getting worse with chemical and labor cost increasing to fight the black algae. | TBD
L-M | Pool Complex Fence | The fence needs to be raised higher so that people will not be able to hop it so easily. We are constantly finding beer bottles, cigarette butts, and condoms on the pool deck. There are also items found at the bottom of the pool. | TBD
H | Leak in the Pool Pipes | After NAS replaced our pool pump motor it was determined that the pool filters were not the problem. The sand that was found at the bottom of the large pool was much finer than the sand in the pool filters. This indicated that there was a leak in one of our return lines. We would need to have NAS come back out and isolate our return lines to potentially find where the leak is coming from. This will be costly but until it is fixed we will slowly be losing water. | TBD
H | Concrete on Pool Deck | Areas on the pool deck need to be evened out and repainted to remove and tripping hazards. Parts of the concrete has started to chip away and sections need to be replaced and repaired. | TBD
Arden Manor Priorities List
Deterding Facilities
| Item | Description | Cost
H | DCC Fascia Boards & Roof | The fascia boards need to be replaced along with the roof. The roof of the DCC is leaking onto the fascia boards causing them to rot. | TBD
H | DAR Roof | One section of the roof was recently repaired due to a leak coming into the snack bar. The entire roof will need to be done with in the next year or two. The shingles are old and deteriorating. | TBD
M | DAR Water Fountain | The water fountain in the Activity Room has been leaking. The maintenance department has attempted to replace several broken elements with no luck. The water fountain will need to be replaced. | TBD
L | Maintenance Shop & Storage | The Maintenance shop is shared with the pool pump and also one truck. This limits how the shop can be organized and how much can be stored. In the future an actual maintenance storage area would be beneficial. | TBD
L | Security Cameras | Security cameras and signage should be installed so that the shop, main office and pool deck can be viewed by cameras. This can help deter people from breaking into our work vehicles and hopping the fence to gain access to the pool. | TBD
M-H | HVAC systems | It is unknown when the last time any of the HVAC systems has been serviced to make sure that they are in good working condition. | TBD
Arden Manor Priorities List
Jonas Larkspur Park
| Item | Description | Cost
H | Bollards & Maintenance Gate | Bollards are in desperate need of replacement. The District could replace all the missing bollards or remove and replace all bollards so that they are uniform. The other option would be to remove all bollards and then replace them with a bollard and chain which would require less bollards. Install maintenance gate on Evelyn that can be locked and secured to keep vehicles out. | Currently getting bids
H | Trees | Mistletoe needs to be removed. Many trees need to be trimmed or weight reduced. There are several dead trees that need to be removed. There are also a few trees that need to have their crowns removed (top of the tree removed). | TBD
H | Softball field | The fence surrounding the baseball field needs some repairs. The infield needs to be cleared of all weeds and debris to be roto tilled. Before grading the field ball field mix would need to be added and spread out. The outfield needs to be leveled off and ruts filled in. If these repairs can be made before spring we could potentially generate revenue from renting out our field. | TBD
M | Soccer Field | The Field needs to be leveled out and have all car ruts removed and filled in. The goal posts need to be repainted. Once fixed we could potentially generate revenue from renting it out again. | TBD
H | Irrigation | Many sprinklers need to be flushed to remove dirt and debris to allow proper water flow. Many sprinkler heads need to be replaced. | TBD
L | Water Fountain | Currently no working water fountain. An ADA compliant fountain should be installed. | TBD
H | Play Structure & Sand Pit | Certified playground inspection needed, Play equipment has heavy use suggesting updated play equipment be installed, Rubber bark level is low and needs to be added, sand box needs sand added | TBD
H | Gazebo | The vine needs to be trimmed back. The Structure should be replaced due to cracking in the wood and the overgrowth of the vine. One table needs to be replaced since there is a crack on the corner and the other two need to have graffiti removed. The concrete slab will eventually need to be redone, there is cracking and high spots. | TBD
L | Tennis Courts | The fence surrounding the tennis court needs some minor repairs. A new gate and 2 nets are needed. The court needs to be resurfaced. | TBD
Arden Manor Priorities List
Jonas Larkspur Park
| Item | Description | Cost
H | Nature Area (not including Pond) | Thinning of saplings and brush is needed. Raising up the branches with trees that need trimming so that there is increased visibility. | TBD
L-M | Pond | Unsure of all the needs of the pond at this time. The pond committee and District Manager are still looking into everything that is needed for this project. | TBD
Arden Manor Administrative Needs
| Item | Description | Cost
H | District Manual | The District Manual is out of date and is in need of updating. Once the manual is updated it should be reviewed by a labor attorney. | TBD
H | Certified Playground Instructor Training | We either need to contract out and have a Certified Playground Safety Inspector visit our parks or we can send a maintenance staff member to get certified in March of 2018 so we can inspect them in house. | TBD
H | District Manager Training | Every year CARPD has a conference that would be beneficial to our small District | TBD

## Priority by H,M,L
Arden Manor Priorities List
| Item | Description | Est. Cost
H | Irrigation (Crabtree) | Replace all broken sprinklers, Replace drip line that is on the perimeter of the park that is currently broken, system flush. Currently working with Jensen on proposed plan and rebates. | TBD
H | Play Structures & sand box (Crabtree) | Certified playground inspection needed, Play equipment has heavy use suggesting updated play equipment be installed, Rubber bark level is low and needs to be added, sand box needs sand added. | TBD
H | Baseball Field (Crabtree) | The fence surrounding the baseball field needs some repairs. Some of the planks of wood used for fan benches and back stop need to be replaced. The infield needs to be cleared of all weeds and debris to be roto tilled. Before grading the field ball field mix would need to be added and spread out. The outfield needs to be leveled off and ruts filled in. If these repairs can be made before spring we could potentially generate revenue from renting out our field. | TBD
H | Trees (Crabtree) | The trees are being trimmed annually | X
H | Irrigation (Deterding) | Replace all broken sprinklers and a system flush | TBD
H | Play Structures (Deterding) | Certified playground inspection needed, Rubber bark level is low and needs to be added. Two Slide sections and barrier/climber up to the slide on the large play structure needs to be replaced. | Getting Estimates
H | Concrete Sidewalk (Deterding) | This job has been completed except for one area needing to be painted. | TBD
H | Trees (Deterding) | The trees are being trimmed annually | X
H | Leak in the Pool Pipes (Deterding Pool) | After NAS replaced our pool pump motor it was determined that the pool filters were not the problem. The sand that was found at the bottom of the large pool was much finer than the sand in the pool filters. This indicated that there was a leak in one of our return lines. We would need to have NAS come back out and isolate our return lines to potentially find where the leak is coming from. This will be costly but until it is fixed we will slowly be losing water. | TBD
H | Concrete on Pool Deck (Deterding Pool) | Many Patches have been taken care of. There are only two raised portions that need to be taken care of. | TBD
H | DCC Fascia Boards & Roof (Deterding) | The fascia boards need to be replaced along with the roof. The roof of the DCC is leaking onto the fascia boards causing them to rot. | TBD
H | DAR Roof (Deterding) | One section of the roof was recently repaired due to a leak coming into the snack bar. The entire roof will need to be done with in the next year or two. The shingles are old and deteriorating. | TBD
H | DAR Ceiling (Deterding) | The ceiling tiles are starting to separate and sag. Recommending putting trim around the perimeter of the ceiling. Estimated Materials $250, estimated labor $200. | X
H | Bollards & Maintenance Gate (Jonas) | bollards were changed over to split rail April 2019 | TOTAL=$40,101
H | Trees (Jonas) | The trees are being trimmed annually | X
H | Softball field (Jonas) | The fence surrounding the baseball field needs some repairs. The infield needs to be cleared of all weeds and debris to be roto tilled. Before grading the field ball field mix would need to be added and spread out. The outfield needs to be leveled off and ruts filled in. If these repairs can be made before spring we could potentially generate revenue from renting out our field. | TBD
H | Irrigation (Jonas) | Many heads still need to be changed. Suggest getting filter for well in the future. We have contacted Odell's to get a quote. | TBD
H | Play Structure & Sand Pit (Jonas) | Certified playground inspection needed, Play equipment has heavy use suggesting updated play equipment be installed, Rubber bark level is low and needs to be added, sand box needs sand added. Estimated 12.5 cubic yards of play sand needed and 4 hours of. | TBD
H | Gazebo (Jonas) | The vine needs to be trimmed back. The Structure should be replaced due to cracking in the wood and the overgrowth of the vine. One table needs to be replaced since there is a crack on the corner and the other two need to have graffiti removed. The concrete slab will eventually need to be redone, there is cracking and high spots. | TBD
H | Nature Area (not including Pond) (Jonas) | Thinning of saplings and brush is needed. Raising up the branches with trees that need trimming so that there is increased visibility. | TBD
H | District Manual | The District Manual is out of date and is in need of updating. Once the manual is updated it should be reviewed by a labor attorney. | TBD
H | Certified Playground Instructor Training | We either need to contract out and have a Certified Playground Safety Inspector visit our parks or we can send a maintenance staff member to get certified in March of 2018 so we can inspect them in house. | TBD
H | District Manager Training | Every year CARPD has a conference that would be beneficial to our small District | TBD
M-H | Small Pool Resurfaced (Deterding) | The small pool needs to be resurfaced due to wear and tear from usage. The bottom of the pool is very porous. Each season is getting worse with chemical and labor cost increasing to fight the black algae. | TBD
M-H | HVAC systems (Deterding) | It is unknown when the last time any of the HVAC systems has been serviced to make sure that they are in good working condition. | TBD
M | Restroom (Crabtree) | One restroom is currently out of order. Sink, toilet paper/paper towel dispensers, door and signage needs to be replaced or repaired. The roof needs to be re-shingled soon due to age. | TBD
M | Water Fountain (Deterding) | The water fountains is not in working order and needs new parts so that both drinking bowls can be used. Depending on what is found we may need a new fountain. The fountain needs 2 pressure regulators for estimated $151 and estimated $35 in labor plus to be roto rooted. Currently getting quote for roto rooting. | $186 plus cost of roto rooting
M | DAR Water Fountain (Deterding) | The water fountain in the Activity Room has been leaking. The maintenance department has attempted to replace several broken elements with no luck. The water fountain will need to be replaced. | $1000 parts & labor
M | Soccer Field (Jonas) | The Field needs to be leveled out and have all car ruts removed and filled in. The goal posts need to be repainted. Once fixed we could potentially generate revenue from renting it out again. | TBD
L | Water Fountains (Crabtree) | There are two water fountains at this park. The fountain by the restroom is not in working order and would need to be replaced. The fountain by the snack bar needs to be repaired. For the fountain near snack bar it needs a pressure regulator and labor. | estimated $150
L | Basketball Court (Crabtree) | Hoop needs to be replaced on one metal post. Could make a full court if the hoops were moved and one backboard was replaced. Lines need to be repainted and nets need to be replaced. | TBD
L | Tennis Courts (Crabtree) | The fence surrounding the tennis courts need some repairs. The tennis court needs new nets and the cracks in the court need to be repaired or possibly to be resurfaced. We would need to have a contractor to come out to advise the District on our options. | TBD
L | Turf Field (Deterding) | The turf field needs holes and missing sections to be replaced and repaired. Signage needs to be posted to prohibit the use of cleats on the field. | TBD
L | Maintenance Shop & Storage (Deterding/Jonas/Crabtree) | The Maintenance shop is shared with the pool pump and also one truck. This limits how the shop can be organized and how much can be stored. In the future an actual maintenance storage area would be beneficial. | TBD
L | Security Cameras (Deterding) | Security cameras and signage should be installed so that the shop, main office and pool deck can be viewed by cameras. This can help deter people from breaking into our work vehicles and hopping the fence to gain access to the pool. | TBD
L | Water Fountain (Jonas) | Currently no working water fountain. An ADA compliant fountain should be installed. Suggesting water testing, filter for well pump and a new fountain. Currently working on estimated cost. | TBD
L | Tennis Courts (Jonas) | The fence surrounding the tennis court needs some minor repairs. A new gate and 2 nets are needed. The court needs to be resurfaced. | TBD
L-M | Pond (Jonas) | Pond is currently being filled as needed | TBD
L-M | Pool Complex Fence (Deterding) | The fence needs to be raised higher so that people will not be able to hop it so easily. We are constantly finding beer bottles, cigarette butts, and condoms on the pool deck. There are also items found at the bottom of the pool. | TBD

## Items community want
2021
Items the Community would like to see
Crabtree
Tennis courts redone
Dog park
full basketball court
new play structures
Exercise equipment around walking path
baseball field fixed
working irrigation
Turf management
Deterding
Turf field fixed
new playstructures
More pool hours
Jonas
Pickle ball courts
working irrigation
bridges around nature area
fix path way around nature area
softball field repaired
new playstructures
better security
2022
Crabtree
Improved Lighting for all Parks
Drinking fountains with dog watering bowls for all parks
Dog Parks at: Crabtree-NW corner of park; Jonas-Larkspur-SW corner of the park
Tennis and Pickleball Court at Crabtree
Futsal court in place of one of the Tennis Court
More regulation Basketball Courts
Skateboard features
Replace the missing play equipment
Lighting in the Crabtree picnic shelter
Place a donation button on the website
Jonas-Larkspur
Working Drinking Fountains
Restroom Facilities
Park Security - emphasis on alcohol & drug use
Install a filter on the well to take out manganese
Develop a District wide tree care plan
Improve the soccer field - gain adhearance of user groups to contracts
Clean up and improve the Maintenance area
Increase summer use by extending hours
Increase summer use by installing shade over the play structures
Have a Futsal court somewhere in the District
Have Community Meetings more often
Develop Public Private Partnerships
Make improvements to the Pond, making it an attraction
Create off leash dog park areas in each park
Resurface the tennis courts making them joint use tennis & pickle ball